## 화면설계
템플릿 디자인 화면 캡쳐로 대체
NavBar
로그인전
Login
회원가입
공지사항
메인화면
거래정보
중개인 소개
중개인 개인 프로필

## WBS
|  |  | 목 | 금 | 토 | 일 | 월 | 화 | 수 | 목
항목 | 세부항목 | 담당 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25
학습 |  | 장현진,최이삭 | 목: 산출물 문서 작성
로그인 | 로그인 , 로그아웃 | 장현진,최이삭 | bar: 목 to 금
회원 | 회원 가입 | 최이삭 | bar: 목 to 일
| 회원 정보 조회 및 수정 | 최이삭 | bar: 목 to 토
매물조회 | 지역별 조회, 수정 | 장현진 | bar: 금 to 토
| 매물 상세조회 | 장현진 | bar: 금 to 토
게시판 | 목록 | 장현진 | bar: 금 to 토
| 상세조회 | 장현진 | bar: 금 to 토
| 등록 | 장현진 | bar: 금 to 토
| 수정 | 장현진 | bar: 금 to 토
| 삭제 | 장현진 | bar: 금 to 토
즐겨찾기 | 지역 즐겨찾기 | 장현진 | bar: 월 to 수
| 중개인 즐겨찾기 | 장현진 | bar: 월 to 수
중개인 | 목록 | 최이삭 | bar: 월 to 수
| 상세 | 최이삭 | bar: 월 to 수
| 좋아요 | 최이삭 | bar: 월 to 수
[9 empty] | 예정 | 완료

## 테이블설계
ERD 화면 캡쳐로 대체

## REST API URL 설계
구분 | 상세 구분 | Method | URL | content-type
로그인 |  | POST | /login | url-encoded
로그아웃 |  | GET | /logout
회원가입 | 등록 | POST | /register
마이페이지 | 조회 | GET | /mypage | application/json
| 수정 | POST | /mypage
즐겨찾기 | 조회 | GET | /userAgentFavorite | application/json
| 수정 | POST | /userAgentFavorite
| 조회 | GET | /userAreaFavorite | application/json
| 수정 | POST | /userAreaFavorite
게시판 | 목록 | GET | /boards | application/json
| 상세 | GET | /boards/1 | application/json
| 등록 | POST | /boards | multipart/form-data
| 수정 | POST(PUT) | /boards
| 삭제 | DELETE | /boards
매물조회 | 목록 | GET | /deals | application/json
| 상세 | GET | /deals/1 | application/json
중개인 | 목록 | GET | /agent | application/json
| 상세 | GET | /agent/1 | application/json
| 좋아요 | PUT | /agent/1

## ResponseEntity 설계
|  | success | fail | error
LoginController | login | 200 | 404 | 500
| logout | 200 |  | 500
BoardController | list | 200 |  | 500
| detail | 200 | 404 | 500
| insert | 200 |  | 500
| update | 200 |  | 500
| delete | 200 |  | 500
HouseController | boardList | 200 |  | 500
| boardDetail | 200 | 404 | 500
UserController | register | 200 |  | 500
| mypage | 200 | 404 | 500
| passwordUpdate | 200 |  | 500
| updateProfile | 200 |  | 500
| userDelete | 200 |  | 500
AgentController | agentList | 200 | 404 | 500
| agentDetail | 200 | 404 | 500
| agentRate | 200 |  | 500

## Vue Component 설계
src 폴더
components
InsertModal.vue
|  | modal | UpdateModal.vue
DetailModal.vue
DetailHouseModal.vue
| page |  | Board.vue
Login.vue
Deal.vue
Footer.vue
Main.vue
Mypage.vue
Navbar.vue
Notify.vue
Pagination.vue
Regiter.vue
Agent.vue
AgentDetail.vue

## Vue Router 설계
Router
router-view